## ProjectBudget
Developing a mobile app - Sumaya
© 2012-2019 Vertex42 LLC
| Project Lead: Ismail in collaboration with Hariharan, Neha, Prabakar & Yokesh | [6 empty] | BUDGET | ACTUAL | Under(Over) | Project Budget Template
| Start Date: 15-02-2024 | [5 empty] | Total | $ 68,468.00 | $ 63,570.00 | $ 4,898.00
|  | Labor |  | Materials |  | Fixed |  |  |  |  | ► More Business Templates
WBS | Tasks | Hrs | Rate | Units | $/Unit | Costs |  | Budget | Actual | Under(Over) | ► Project Management Templates
1 | Developing a mobile app - Sumaya | [9 empty] | ► More Budget Templates
1.1 | Delivery of an online shopping app | [6 empty] | 48916 | 47132 | 1784
1.1.1 | Project Management | 3372 | [5 empty] | $ 9,584.00 | $ 9,304.00 | $ 280.00
1.1.1.1 | Define Project Scope | 144 | $12.00 |  |  |  |  | 1728 | 1728 | -
1.1.1.1.1 | Review Stakeholder Requirements | 48 | [5 empty] | - |  | -
1.1.1.1.2 | Identify Project Constraints | 48 | [5 empty] | - |  | -
1.1.1.1.3 | Define Project Deliverables | 48 | [5 empty] | - |  | -
1.1.1.2 | Develop Project Plan | 48 | $12.00 |  |  |  |  | 576 | 576 | -
1.1.1.2.1 | Define Project Timeline | 8 | [5 empty] | - |  | -
1.1.1.2.2 | Allocate Project Resources | 16 | [5 empty] | - |  | -
1.1.1.2.3 | Review and Approval of Project Plan | 24 | [5 empty] | - |  | -
1.1.1.3 | Team Kick-off and Training | 440 | $12.00 |  |  | $2,000.00 |  | 7280 | 7000 | 280
1.1.1.3.1 | Conduct Team Introduction | 40 | [5 empty] | - |  | -
1.1.1.3.2 | Provide Project Training | 400 | [5 empty] | - |  | -
1.1.1.4 | Project Execution | 2640 | [5 empty] | - |  | -
1.1.1.5 | Project Monitoring & Control | 2640 | [5 empty] | - |  | -
1.1.1.6 | Risk Management | 2640 | [5 empty] | - |  | -
1.1.2 | Requirement Analysis | 288 | [5 empty] | $ 3,456.00 | $ 3,168.00 | $ 288.00
1.1.2.1 | Stakeholder Interviews | 240 | $12.00 |  |  |  |  | 2880 | 2600 | 280
1.1.2.1.1 | Schedule Stakeholder Meetings | 72 | [5 empty] | - |  | -
1.1.2.1.2 | Conduct Stakeholder Interviews | 168 | [5 empty] | - |  | -
1.1.2.2 | Market Research | 48 | $12.00 |  |  |  |  | 576 | 568 | 8
1.1.2.2.1 | Identify Target Audience | 24 | [5 empty] | - |  | -
1.1.2.2.2 | Analyze Market Trends | 24 | [5 empty] | - |  | -
1.1.3 | Design | 360 | [5 empty] | $ 11,200.00 | $ 10,000.00 | $ 1,200.00
1.1.3.1 | UI/UX Design | 200 | $20.00 |  |  | $2,000.00 |  | 6000 | 6000 | -
1.1.3.1.1 | Wireframe Development | 80 | [5 empty] | - |  | -
1.1.3.1.2 | Prototype Creation | 120 | [5 empty] | - |  | -
1.1.3.2 | Database Design | 160 | $20.00 |  |  | $2,000.00 |  | 5200 | 4000 | 1200
1.1.3.2.1 | Database Schema Planning | 80 | [5 empty] | - |  | -
1.1.3.2.2 | Data Model Implementation | 80 | [5 empty] | - |  | -
1.1.4 | Development | 300 | [5 empty] | $ 9,000.00 | $ 9,000.00 | $ -
1.1.4.1 | Frontend Development (ios & android) | 140 | $20.00 |  |  | $1,500.00 |  | 4300 | 5000 | -700
1.1.4.1.1 | UI Coding | 60 | [5 empty] | - |  | -
1.1.4.1.2 | Responsive Design Implementation | 80 | [5 empty] | - |  | -
1.1.4.2 | Backend Development | 160 | $20.00 |  |  | $1,500.00 |  | 4700 | 4000 | 700
1.1.4.2.1 | Server Setup and Configuration | 80 | [5 empty] | - |  | -
1.1.4.2.2 | API Development | 80 | [5 empty] | - |  | -
1.1.5 | Testing | 160 | [5 empty] | $ 4,660.00 | $ 4,500.00 | $ 160.00
1.1.5.1 | Unit Testing | 80 | $13.50 |  |  | $1,000.00 |  | 2080 | 2000 | 80
1.1.5.1.1 | Code Unit Testing | 40 | [5 empty] | - |  | -
1.1.5.1.2 | UI Unit Testing | 40 | [5 empty] | - |  | -
1.1.5.2 | Integration Testing | 80 | $13.50 |  |  | $1,500.00 |  | 2580 | 2500 | 80
1.1.5.2.1 | API Integration Testing | 32 | [5 empty] | - |  | -
1.1.5.2.2 | System Integration Testing | 32
1.1.5.2.3 | QC approval for Product release | 16 | [5 empty] | - |  | -
1.1.6 | Deployment | 104 | [5 empty] | $ 7,560.00 | $ 7,800.00 | $ (240.00)
1.1.6.1 | Deployment Plan | 56 | $15.00 |  |  | $1,000.00 |  | 1840 | 2000 | -160
1.1.6.1.1 | Plan Server Configuration | 24 | [5 empty] | - |  | -
1.1.6.1.2 | Implement Rollback Strategy | 32 | [5 empty] | - |  | -
1.1.6.2 | Server Deployment | 48 | $15.00 |  |  | $2,000.00 |  | 2720 | 3800 | -1080
1.1.6.2.1 | Configure Hosting Environment | 24 |  | 2 | $1,500.00 |  |  | 3000 | 2000 | 1000
1.1.6.2.2 | Deploy Application | 24 | [5 empty] | - |  | -
1.1.7 | Training and Documentation | 192 | [5 empty] | $ 2,304.00 | $ 2,208.00 | $ 96.00
1.1.7.1 | User Training | 112 | $12.00 |  |  |  |  | 1344 | 1308 | 36
1.1.7.1.1 | Conduct User Workshops | 64 | [5 empty] | - |  | -
1.1.7.1.2 | Provide Training Materials | 48 | [5 empty] | - |  | -
1.1.7.2 | Technical Documentation | 80 | $12.00 |  |  |  |  | 960 | 900 | 60
1.1.7.2.1 | Create User Manuals | 80 | [5 empty] | - |  | -
1.1.8 | Project Closure | 96 | [5 empty] | $ 1,152.00 | $ 1,152.00 | $ -
1.1.8.1 | Final review of deliverables | 40 | $12.00 |  |  |  |  | 480 | $ 480.00 | -
1.1.8.2 | Stakeholder approval of sign off | 24 | $12.00 |  |  |  |  | 288 | $ 288.00 | -
1.1.8.3 | Project debrief - record lessons learnt | 16 | $12.00 |  |  |  |  | 192 | $ 192.00 | -
1.1.8.4 | Storage of artifacts into repository | 16 | $12.00 |  |  |  |  | 192 | $ 192.00 | -
1.2 | Marketing and Promotion | 368 | [5 empty] | $ 8,416.00 | $ 8,038.00 | $ 378.00
1.2.1 | Marketing Strategy | 208 | [5 empty] | 2496 | 2376 | $ 120.00
1.2.1.1 | Develop Marketing Plan | 48 | $12.00 |  |  |  |  | 576 | 500 | 76
1.2.1.2 | Implement Social Media Campaigns | 160 | $12.00 |  |  |  |  | 1920 | 1892 | 28
1.2.2 | Social Media Promotion | 64 | [5 empty] | 1768 | 1568 | 200
1.2.2.1 | Create Engaging Content | 32 | $12.00 |  |  | $1,000.00 |  | 1384 | 1200 | 184
1.2.2.2 | Schedule and Post Content | 32 | $12.00 |  |  |  |  | 384 | 368 | 16
1.2.3 | Advertising Campaigns | 96 | [5 empty] | 4152 | 4094 | 58
1.2.3.1 | Design Advertisements | 48 | $12.00 |  |  |  |  | 576 | 594 | -18
1.2.3.2 | Launch Ad Campaigns | 48 | $12.00 | 5 | $200.00 | $2,000.00 |  | 3576 | 3500 | 76
1.3 | Maintenance and Support | 928 | [5 empty] | $ 11,136.00 | $ 8,400.00 | $ 2,736.00
1.3.1 | Bug Fixes and Updates | 688 | [5 empty] | 8256 | 6000 | 2256
1.3.1.1 | Identify and Resolve Bugs | 344 | $12.00 |  |  |  |  | 4128 | 3000 | 1128
1.3.1.2 | Implement System Updates - Ongoing | 344 | $12.00 |  |  |  |  | 4128 | 3000 | 1128
1.3.2 | Customer Support | 240 | $12.00 |  |  |  |  | 2880 | 2400 | 480
TEMPLATE ROWS
Use the rows listed below by Copying and Pasting (or Copy and Insert), depending on which WBS level you want to use.
1 | [ Task Category ] | [5 empty] | $- | $- | $-
1.1 | [ Level 2 Task ] | [5 empty] | - |  | -
1.1.1 | [ Level 3 Task ] | [5 empty] | - |  | -
1.1.1.1 | [ Level 4 task ] | [5 empty] | - |  | -
1.1.1.1.1 | [ Level 5 task ] | [5 empty] | - |  | -
Note on A8: WBS (Work Breakdown Structure): Each level uses a different formula to display the correct outline numbering. Copy the cell from the Template rows at the bottom of the worksheet and paste it as needed to define different task levels. Level 1: 1 Level 2: 1.1 Level 3: 1.1.1
Note on H8: Fixed Costs: Costs that may not fall under Labor and Materials, or for cases where you want to enter a fixed amount rather than calculating the Budget amount.

## Help
HELP |  | © 2012-2019 Vertex42.com
https://www.vertex42.com/ExcelTemplates/project-budget.html
Terms of Use
Do not submit copies or modifications of this template to any website or online template gallery. Please review the following license agreement to learn how you may or may not use this template. Thank you.
See License Agreement
https://www.vertex42.com/licensing/EULA_privateuse.html
Instructions / Tips
In this worksheet, the Budget amount is calculated from the Labor, Materials, and Fixed Costs columns. After defining your budget, you can hide these columns, or you could hide just the unused columns.
When adding new rows, copy an existing row and insert the copied row, so that the formulas in the grey WBS, Budget, and Under(Over) columns are copied. You can also copy a row from the list of template rows at the bottom of the worksheet.
Each WBS level in column A (1, 1.1, 1.1.1, etc.) uses a different formula. To change the WBS level for a task, you can copy and paste the cell containing the formula that you need from the list of template rows at the bottom of the worksheet. The indent for the Task column can be changed via cell formatting.
The Level 1 categories contain SUM() formulas in the Budget and Actual columns that should be verified for accuracy after inserting new rows. Check these formulas to ensure that the SUM() formula is referencing the correct range of cells.
Any time you add or remove a Level 1 category, you will need to update the formulas for the Total section at the top of the worksheet, to make sure that the Total correctly sums the correct cells.
After adding new categories, you may need to redefine the print area to include the new rows. In Excel 2003, go to File > Print Area > Set Print Area. In Excel 2010 go to Page Layout > Print Area > Set Print Area.
If you see "#####" in a cell, it means you need to widen the column to see the value.

## Sheet1
Development Costs:
Salaries/Wages: Include the cost of hiring developers, designers, QA testers, and project managers. Estimate based on hourly rates or monthly salaries.
Software Licenses: Cost of purchasing development tools, IDEs, frameworks, and other software required for app development.
Training: Budget for any training sessions or courses required for the team to acquire necessary skills.
Freelancer/Contractor Fees: If outsourcing certain tasks or hiring freelancers, allocate funds for their fees.
Infrastructure Costs:
Hosting: Expenses for hosting the app on servers. Consider cloud hosting providers like AWS, Google Cloud, or Azure.
Domain Registration: Cost of registering a domain name for the app's website.
SSL Certificate: Secure Socket Layer certificate for ensuring data security and encryption.
Database: Cost of database services, if not included in hosting fees.
Third-Party Services:
Payment Gateway Fees: Charges for integrating payment gateways like Stripe, PayPal, or Square.
Analytics Tools: Cost of integrating analytics platforms like Google Analytics or Mixpanel.
SMS/Email Services: If sending notifications or alerts, include expenses for SMS or email service providers.
Design and User Experience:
Graphic Design: Expenses for hiring graphic designers for UI/UX design, branding, and logo creation.
Prototyping Tools: Cost of prototyping software or tools for creating wireframes and mockups.
Marketing and Promotion:
App Store Fees: Charges for listing the app on app stores like Apple App Store and Google Play Store.
Digital Marketing: Budget for online advertising, social media marketing, influencer collaborations, and content creation.
App Store Optimization (ASO): Investment in ASO strategies to improve app visibility and downloads.
Maintenance and Support:
Ongoing Development: Budget for future updates, feature enhancements, and bug fixes.
Customer Support: Funds for providing customer support services through email, chat, or phone.
Contingency:
Buffer: Allocate a percentage of the total budget as a contingency fund to cover unexpected expenses or scope changes.