## Project Budget
Developing an online shopping app - Sumaya
Project Budget: $70,000 | Project Info | [6 empty] | Budget Summary |  |  | Project Budget Templates
|  | Project Lead: | Ismail in collaboration with Hariharan, Neha, Prabakar & Yokesh |  |  |  | [42] | Budget | Actual | Under(Over) | © 2019 Vertex42 LLC
|  | Start Date: | 2024-03-01 |  |  |  |  | 68468 | 63570 | 4898 | ► More Business Finance Templates
► Project Management Templates
| Labor |  | Materials |  | Fixed Costs | [5 empty] | ► More Business Templates
Tasks | Hrs | Rate | Units | $/Unit | Material | Travel | Other | Budget | Actual | Under(Over)
Delivery of Online shopping Mobile app | [7 empty] | 48916 | 47132 | 1784 | ◄ Verify SUBTOTAL formulas after inserting new rows.
Project Management | 632 | 12 |  |  |  |  | 1720 | 9584 | 9304 | 280
Requirement Analysis | 288 | 11 | [5 empty] | 3456 | 3168 | 288
Design | 360 | 20 |  |  |  |  | 2800 | 11200 | 10000 | 1200
Development | 300 | 21 |  |  | 300 |  | 2400 | 9000 | 9000 | 0
Testing | 160 | 14 |  |  |  |  | 2260 | 4660 | 4500 | 160
Deployment | 104 | 15 | 2 | 1700 |  |  | 2840 | 7560 | 7800 | -240
Training and Documentation | 192 | 11.5 | [5 empty] | 2304 | 2208 | 96
Project Closure | 96 | 12 | [5 empty] | 1152 | 1152 | 0
Marketing and Promotion | [7 empty] | 8416 | 8038 | 378
Marketing Strategy | 198 | 12 | [5 empty] | 2496 | 2376 | 120
Social Media Promotion | 64 | 12 |  |  |  |  | 800 | 1768 | 1568 | 200
Advertising Campaigns | 92 | 12 | 5 | 200 |  |  | 1990 | 4152 | 4094 | 58
Maintenance and Support | [7 empty] | 11136 | 8400 | 2736
Bug Fixes and Updates | 500 | 12 | [5 empty] | 8256 | 6000 | 2256
Customer Support | 200 | 12 | [5 empty] | 2880 | 2400 | 480

## Help
Template Help
Visit the Project Budget Template Page >
About This Template
This version of the project budget template was designed with a new look and it provides multiple columns for fixed costs. Also, instead of using the Labor, Materials, and Fixed Costs columns to calculate the Budgeted amount, these columns are used to calculate the Actual amount.
Entering Budget and Actual Amounts
In this worksheet, the Actual amount is calculated from the Labor, Materials, and Fixed Costs columns. This means that you manually enter the Budget value and you use the Labor, Materials, and Fixed Costs columns to enter actual spent amounts.
When Adding New Rows
The Phase/Category Title rows contain SUBTOTAL(9,...) formulas in the Budget and Actual columns that should be verified for accuracy after inserting new rows. Check these formulas to ensure that they reference the correct range of cells.
Note: The SUBTOTAL(9,…) function is the same as the SUM(…) function except that using SUBTOTAL() ignores cells containing other SUBTOTAL() formulas. This allows the grand-total at the top to sum all budget values while ignoring the subtotals.
Cell containing "#####"
If you see "#####" in a cell, it means you need to widen the column to see the value, or reduce the font size for that cell.

## ©
Project Budget Template
By Vertex42.com
https://www.vertex42.com/ExcelTemplates/project-budget.html
© 2019 Vertex42 LLC
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery.
Please review the following license agreement to learn how you may or may not use this template. Thank you.
License Agreement
https://www.vertex42.com/licensing/EULA_privateuse.html
Do not delete this worksheet.